## Summary sheet for release versi
cQube Release 4.0-alpha Test Script Execution Summary Sheet
Test Name | Planned Start Date | Test Happened Date | Environment of Test Activity | Type of testing Manual / Automation | Total number of Test cases / Scripts prepared | No Of Test Cases Pending | No. Of Test Cases Executed | No Of Passed Test Cases | No. of Failed Test cases | Pass % | Fail % | Comment
Smoke Testing of Azure(Installation, Ingestion_api, Data Processing)(State) | 2022-09-26 | 2022-09-26 | Testing Environment | Manual | 91 | 3 | 85 | 81 | 4 | 95.29% | 4.706%
Smoke Testing of S3(Installation, Ingestion_api, Data Processing)(State) | 2022-09-26 | 2022-09-26 | Testing Environment | Manual | 91 | 7 | 84 | 83 | 1 | 98.81% | 1.19%
Smoke Testing of On-premise(Installation, Ingestion_api, Data Processing)(State) | 2022-09-26 | 2022-09-26 | Testing Environment | Manual | 91 | 7 | 84 | 83 | 1 | 98.81% | 1.19%
Functional Testing of S3(Installation,Data Processing )(National) | 2022-09-26 | 2022-09-26 | Testing Environment | Manual | 47 | 0 | 47 | 47 | 0 | 100% | 0%
Functional Testing of Azure(Installation, Ingestion_api, Data Processing )(State) | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 181 | 58 | 123 | 118 | 5 | 95.93% | 4.065%
Functional Testing of S3(Installation, Ingestion_api, Data Processing )(State) | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 181 | 58 | 123 | 118 | 5 | 95.93% | 4.065%
Smoke Testing of UI (State) | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 337 | 0 | 337 | 337 | 0 | 100% | 0%
Functional Testing of UI (State) | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 934 | 31 | 903 | 849 | 54 | 94.02% | 5.98%
Functional Testing of UI(National) | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 576 | 0 | 576 | 573 | 3 | 99.48% | 0.5208%
S3 upgradation from 3.7 to 4.0 | 2022-09-28 | 2022-09-28 | Testing Environment | Manual | 45 | 0 | 45 | 45 | 0 | 100% | 0%
Total Number of Resolved defects | https://github.com/orgs/Sunbird-cQube/projects/5/views/5?filterQuery=milestone%3A%22cQube+v4.0+Alpha%22+status%3A%22Live+%F0%9F%9A%80%22%2C%22QA+Complete+%F0%9F%91%8C%F0%9F%8F%BD%22+label%3A%22Bug-Blockers%22%2C%22Bug-Critical%22%2C%22Bug-Major%22%2C%22Bug-Minor%22